## Initiatives
Initiative ID | Initiative name | Description | Business unit | Start | Baseline end | Revised end | Planned phase at year end | Current phase | Value baseline | Value baseline start year | Value revised | Value revised start year | Approved budget (reporting year) | Budget used or forecast | Reason for change | Notes
INS-001 | Planning Scheduler Redesign | Extend the ledger used by Operations. | Operations | 2025-02-07 | 2026-06-30 | Delivered | Delivered | Delivered | 8.6 | 2026 | 7.7 | 2028 | 14.2 | 7.3
INS-002 | Billing Toolkit Launch | Standardise the toolkit used by Customer Service. | Customer Service | 2025-10-07 | 2026-11-30 | 2026-12-31 | Delivered | Execution | 14.9 | 2028 | 20 | 2029 | 15.7 | 4 | Scope extended after design review
INS-003 | Purchasing Scheduler Automation | Extend the portal used by Finance. | Finance | 2025-08-16 | 2026-08-31 |  | Delivered | Deployment | 35.8 | 2027 | 46.1 | 2026 | 22.1 | 9.2
INS-004 | Service Desk Catalogue Migration | Standardise the dashboard used by People. | People | 2024-11-19 | 2026-03-31 | Q4-2026 | Delivered | Execution |  |  |  |  | 2.8 | 0.8 | Faster delivery after reuse of an existing component
INS-005 | Customer Catalogue Upgrade | Standardise the forecasting used by Technology. | Technology | Q3-2025 | 2026-06-30 | No change | Delivered | Initiation | 21.3 | 2027 | 21.1 | 2028 | 5.9 | 2.9
INS-006 | Payroll Toolkit Upgrade | Introduce the portal used by Supply Chain. | Supply Chain | 2024-02-13 | 2026-02-28 | ON HOLD | Delivered | On hold | 45.8 | 2026 | 44.4 | 2028 | 2.8 | 1 | Regulatory review added a step | Reviewed at the quarterly portfolio meeting.
INS-007 | Fleet Records Launch | Standardise the scheduler used by Sales & Marketing. | Sales & Marketing | 2025-01-02 | Q4-2026 | Cancelled | Delivered | Cancelled | 35.3 | 2028 | 23.3 | 2029 | 5 | 1.7 | Regulatory review added a step
INS-008 | Safety Data Model Rollout | Simplify the forecasting used by Operations. | Operations | 2026-01-16 | 2027-03-31 | Q4-2026 | Deployment | Delivered |  |  | 8.7 | 2028 | 21.9 | 9.8 | Scope extended after design review
INS-009 | Asset Ledger Rollout | Introduce the data model used by Customer Service. | Customer Service | 2026 | 2027-09-30 | 2027-12-31 | Execution | Execution | 22.2 | 2026 | 28.5 | 2028 | 19.2 | 19.3 | Faster delivery after reuse of an existing component
INS-010 | Planning Catalogue Redesign | Standardise the data model used by Finance. | Finance | Q4-2026 | 2027-06-30 | 2027-03-31 | Deployment | Execution | 23.4 | 2026 |  |  | 9.6 | 9.4 | Supplier lead times longer than planned
INS-011 | Inventory Workflow Upgrade | Extend the catalogue used by People. | People | 2026-08-20 | 2027-12-31 | No change | Execution | Initiation | 16.9 | 2028 | 13.2 | 2026 |  | 0.6
INS-012 | Purchasing Workflow Launch | Simplify the portal used by Technology. | Technology | 2026-12-04 | 2028-03-31 |  | Initiation | Not started |  |  |  |  | 15.1 | 15.4 |  | Reviewed at the quarterly portfolio meeting.
INS-013 | Safety Dashboard Migration | Standardise the workflow used by Supply Chain. | Supply Chain | 2025-11-22 | 2027-06-30 | On hold | Execution | On hold | 40.2 | 2028 | 25.6 | 2026 | 3 |  | Dependency on another initiative
INS-014 | Workforce Scheduler Launch | Standardise the scheduler used by Sales & Marketing. | Sales & Marketing | 2026-08-21 | Q4-2027 | Cancelled | Initiation | Cancelled | 39.2 | 2028 | 37.9 | 2028 | 3.6 | 2.1 | Supplier lead times longer than planned
INS-015 | Asset Forecasting Modernisation | Introduce the scheduler used by Operations. | Operations | Q4-2025 | 2026-06-30 | DELIVERED | Delivered | Delivered | 16.6 | 2028 | 22.2 | 2026 | 10.2 | 7.2
INS-016 | Workforce Catalogue Consolidation | Simplify the records used by Customer Service. | Customer Service | 2026-05-23 | 2026-11-30 | Q2-2027 | Delivered | Execution |  |  | 4.9 | 2029 | 19.2 | 18.4 | Resources moved to a higher-priority initiative
INS-017 | Field Service Dashboard Upgrade | Simplify the toolkit used by Finance. | Finance | 2026-05-16 | 2026-11-30 | 2027-04-30 | Delivered | Execution | 50.4 | 2028 | 46.8 | 2027 | 7.4 | 5.4 | Dependency on another initiative
INS-018 | Onboarding Dashboard Redesign | Standardise the scheduler used by People. | People | 2024 | 2026-03-31 | 2026-06-30 | Delivered | Execution | 22.2 | 2028 | 25.3 | 2028 | 6 | 2.8 | Testing found integration issues | Reviewed at the quarterly portfolio meeting.
INS-019 | Service Desk Toolkit Migration | Standardise the catalogue used by Technology. | Technology | 2027-04-08 | 2028-03-31 |  | Initiation | Not started | 24.3 | 2026 | 33.5 | 2027 | 21 | 16
INS-020 | Contract Records Consolidation | Introduce the dashboard used by Supply Chain. | Supply Chain | Q4-2024 | 2026-11-30 | Q2-2027 | Delivered | Execution |  |  |  |  | 4.1 | 3.6 | Faster delivery after reuse of an existing component
INS-021 | Quality Catalogue Migration | Introduce the data model used by Sales & Marketing. | Sales & Marketing | 2025-05-28 | Q1-2026 | ON HOLD | Delivered | On hold | 47.5 | 2027 | 56 | 2029 | 0.5 | 0.4 | Scope extended after design review
INS-022 | Workforce Ledger Launch | Simplify the catalogue used by Operations. | Operations | 2027-01-19 | 2027-12-31 | no change | Execution | Initiation | 7.1 | 2027 | 7.8 | 2028
INS-023 | Asset Catalogue Redesign | Extend the portal used by Customer Service. | Customer Service | 2025-12-17 | 2026-06-30 | Delivered | Delivered | Delivered | 45.2 | 2028 | 37.6 | 2028 | 8.8 | 5.9
INS-024 | Fleet Portal Launch | Introduce the ledger used by Finance. | Finance | 2026-11-04 | 2027-09-30 | Q2-2028 | Execution | Execution |  |  | 4.9 | 2027 | 1.1 | 0.9 | Resources moved to a higher-priority initiative | Reviewed at the quarterly portfolio meeting.
INS-025 | Learning Records Upgrade | Introduce the records used by People. | People | Q1-2026 | 2026-11-30 | 2027-07-31 | Delivered | Execution | 9.4 | 2026 | 9.2 | 2026 | 16.9 | 15.1 | Supplier lead times longer than planned
INS-026 | Service Desk Workflow Rollout | Standardise the data model used by Technology. | Technology | 2025-08-13 | 2026-02-28 | On hold | Delivered | On hold | 23.9 | 2028 | 14.8 | 2027 | 1.3 |  | Testing found integration issues
INS-027 | Inventory Scheduler Upgrade | Extend the portal used by Supply Chain. | Supply Chain | 2026 | 2027-03-31 | 2026-12-31 | Deployment | Delivered | 41.9 | 2027 | 42.8 | 2027 | 2.1 | 1.8 | Testing found integration issues
INS-028 | Workforce Records Consolidation | Introduce the dashboard used by Sales & Marketing. | Sales & Marketing | 2024-06-10 | Q2-2026 | Delivered | Delivered | Delivered |  |  |  |  | 5.2 | 4.3
INS-029 | Reporting Dashboard Redesign | Introduce the ledger used by Operations. | Operations | 2025-07-09 | 2026-02-28 | On hold | Delivered | On hold | 12 | 2026 | 12 | 2026 | 19.1 | 16.4 | Scope extended after design review
INS-030 | Fleet Catalogue Automation | Replace the forecasting used by Customer Service. | Customer Service | Q4-2024 | 2026-06-30 | DELIVERED | Delivered | Delivered | 21.2 | 2028 |  |  | 15.8 | 17.7 |  | Reviewed at the quarterly portfolio meeting.
INS-031 | Learning Dashboard Redesign | Standardise the dashboard used by Finance. | Finance | 2026-03-10 | 2027-12-31 | No change | Execution | Initiation | 31 | 2028 | 20.1 | 2027 | 9.9 | 7.1
INS-032 | Quality Records Migration | Extend the ledger used by People. | People | 2025-09-07 | 2026-10-31 | Cancelled | Delivered | Cancelled |  |  | 5.7 | 2029 | 19.2 | 6.5 | Faster delivery after reuse of an existing component
INS-033 | Learning Catalogue Modernisation | Extend the dashboard used by Technology. | Technology | 2025-06-17 | 2026-02-28 | ON HOLD | Delivered | On hold | 23.3 | 2028 | 31.3 | 2029 |  | 1.7 | Scope extended after design review
INS-034 | Supplier Records Launch | Introduce the data model used by Supply Chain. | Supply Chain | 2024-08-21 | 2026-03-31 | 2026-10-31 | Delivered | Execution | 55.9 | 2028 | 76.6 | 2027 | 17.7 | 15.9 | Scope extended after design review
INS-035 | Payroll Toolkit Automation | Extend the dashboard used by Sales & Marketing. | Sales & Marketing | Q1-2026 | Q4-2026 | 2027-03-31 | Delivered | Execution | 48.5 | 2027 | 46.2 | 2029 | 19.7 | 16 | Faster delivery after reuse of an existing component
INS-036 | Field Service Ledger Automation | Standardise the ledger used by Operations. | Operations | 2026 | 2026-08-31 |  | Delivered | Deployment |  |  |  |  | 16.9 | 13 |  | Reviewed at the quarterly portfolio meeting.
INS-037 | Purchasing Forecasting Automation | Extend the portal used by Customer Service. | Customer Service | 2026-03-19 | 2027-03-31 | 2026-12-31 | Deployment | Delivered | 7.2 | 2028 | 5.3 | 2026 | 3.9 | 3.8 | Resources moved to a higher-priority initiative
INS-038 | Safety Dashboard Rollout | Replace the records used by Finance. | Finance | 2027-04-12 | 2028-03-31 |  | Initiation | Not started | 22.7 | 2026 | 18.7 | 2028 | 20.3 | 8.3
INS-039 | Purchasing Toolkit Consolidation | Simplify the records used by People. | People | 2025-12-03 | 2026-11-30 | 2027-04-30 | Delivered | Execution | 46.6 | 2028 | 42.8 | 2026 | 21.3 |  | Dependency on another initiative
INS-040 | Fleet Data Model Redesign | Introduce the data model used by Technology. | Technology | Q4-2025 | 2027-09-30 | Q1-2028 | Execution | Execution |  |  | 1.7 | 2027 | 14.1 | 12.6 | Resources moved to a higher-priority initiative
INS-041 | Workforce Portal Modernisation | Introduce the toolkit used by Supply Chain. | Supply Chain | 2026-07-27 | 2027-09-30 | 2028-02-29 | Execution | Execution | 51.6 | 2027 | 57 | 2029 | 18.3 | 16.2 | Regulatory review added a step
INS-042 | Field Service Ledger Consolidation | Introduce the forecasting used by Sales & Marketing. | Sales & Marketing | 2024-10-16 | Q2-2026 | DELIVERED | Delivered | Delivered | 32.2 | 2028 | 45 | 2029 | 15.4 | 15.3 |  | Reviewed at the quarterly portfolio meeting.
INS-043 | Onboarding Ledger Launch | Replace the portal used by Operations. | Operations | 2025-09-12 | 2027-06-30 | 2027-02-28 | Deployment | Execution | 22.2 | 2026 | 25.2 | 2026 | 19.7 | 17.5 | Regulatory review added a step
INS-044 | Fleet Catalogue Consolidation | Simplify the dashboard used by Customer Service. | Customer Service | 2026-04-19 | 2028-03-31 |  | Initiation | Not started
INS-045 | Field Service Forecasting Migration | Extend the catalogue used by Finance. | Finance | 2026 | 2027-09-30 | 2028-01-31 | Execution | Execution | 39 | 2028 | 30 | 2029 | 11.2 | 9 | Resources moved to a higher-priority initiative
INS-046 | Payroll Dashboard Redesign | Standardise the catalogue used by People. | People | 2026-08-17 | 2027-06-30 | 2027-02-28 | Deployment | Execution | 2.1 | 2028 | 2.5 | 2029 | 21.5 | 18.8 | Resources moved to a higher-priority initiative
INS-047 | Planning Scheduler Automation | Standardise the catalogue used by Technology. | Technology | 2027-01-10 | 2027-09-30 | 2028-01-31 | Execution | Execution | 45.3 | 2027 | 41.7 | 2029 | 15.1 | 9.6 | Testing found integration issues
INS-048 | Payroll Data Model Automation | Introduce the portal used by Supply Chain. | Supply Chain | 2025-05-13 | 2026-11-30 | Q2-2027 | Delivered | Execution |  |  | 5.8 | 2026 | 19.3 | 13.8 | Resources moved to a higher-priority initiative | Reviewed at the quarterly portfolio meeting.
INS-049 | Billing Records Redesign | Replace the scheduler used by Sales & Marketing. | Sales & Marketing | 2026-09-20 | Q1-2028 |  | Initiation | Not started | 1.6 | 2027 | 1.4 | 2028 | 3.6 | 2.8
INS-050 | Workforce Toolkit Upgrade | Replace the workflow used by Operations. | Operations | Q2-2025 | 2026-06-30 | Delivered | Delivered | Delivered | 52.3 | 2026 |  |  | 5.1 | 1.5
INS-051 | Service Desk Workflow Launch | Standardise the records used by Customer Service. | Customer Service | 2026-06-01 | 2027-12-31 | No change | Execution | Initiation | 10.4 | 2027 | 6.9 | 2029 | 12.9 | 12.2
INS-052 | Inventory Dashboard Rollout | Simplify the forecasting used by Finance. | Finance | 2025-10-13 | 2027-09-30 | Q1-2028 | Execution | Execution |  |  |  |  | 14.2 |  | Dependency on another initiative
INS-053 | Billing Forecasting Modernisation | Replace the forecasting used by People. | People | 2025-09-10 | 2026-11-30 | 2026-12-31 | Delivered | Execution | 25.5 | 2027 | 33.4 | 2026 | 11.6 | 10.2 | Dependency on another initiative
INS-054 | Field Service Data Model Upgrade | Replace the data model used by Technology. | Technology | 2026 | 2027-12-31 | no change | Execution | Initiation | 37.6 | 2027 | 35.6 | 2026 | 4.5 | 1 |  | Reviewed at the quarterly portfolio meeting.
INS-055 | Learning Workflow Upgrade | Simplify the scheduler used by Supply Chain. | Supply Chain | Q3-2026 | 2027-09-30 | 2027-10-31 | Execution | Execution | 46.5 | 2027 | 46.2 | 2026 |  | 0.1 | Scope extended after design review
INS-056 | Payroll Workflow Launch | Introduce the scheduler used by Sales & Marketing. | Sales & Marketing | 2025-06-09 | Q1-2026 | Q4-2026 | Delivered | Execution |  |  | 2.9 | 2026 | 9.2 | 5.7 | Resources moved to a higher-priority initiative
INS-057 | Contract Forecasting Consolidation | Standardise the portal used by Operations. | Operations | 2025-04-21 | 2026-08-31 |  | Delivered | Deployment | 58 | 2027 | 79.3 | 2029 | 23.7 | 23.1
INS-058 | Planning Dashboard Modernisation | Replace the portal used by Customer Service. | Customer Service | 2027-02-09 | 2027-12-31 | no change | Execution | Initiation | 13.4 | 2027 | 15.5 | 2029 | 15.9 | 5.4
INS-059 | Customer Workflow Migration | Simplify the dashboard used by Finance. | Finance | 2026-12-18 | 2028-03-31 |  | Initiation | Not started | 22 | 2028 | 27.9 | 2029 | 24.1 | 23.9
INS-060 | Field Service Data Model Migration | Extend the dashboard used by People. | People | Q1-2025 | 2026-06-30 | DELIVERED | Delivered | Delivered |  |  |  |  | 9 | 7.4 |  | Reviewed at the quarterly portfolio meeting.
INS-061 | Billing Workflow Migration | Simplify the ledger used by Technology. | Technology | 2026-02-15 | 2027-09-30 | 2027-11-30 | Execution | Execution | 17.6 | 2027 | 15.3 | 2028 | 15.2 | 7 | Testing found integration issues
INS-062 | Asset Portal Launch | Replace the scheduler used by Supply Chain. | Supply Chain | 2027-06-09 | 2028-03-31 |  | Initiation | Not started | 48.9 | 2026 | 35.4 | 2028 | 8.5 | 6.2
INS-063 | Supplier Records Migration | Extend the data model used by Sales & Marketing. | Sales & Marketing | 2025 | Q4-2026 | 2027-03-31 | Delivered | Execution | 2.6 | 2027 | 2.8 | 2028 | 8.2 | 7.3 | Faster delivery after reuse of an existing component
INS-064 | Planning Dashboard Automation | Introduce the catalogue used by Operations. | Operations | 2025-09-19 | 2026-11-30 | Q2-2027 | Delivered | Execution |  |  | 1.9 | 2028 | 6.6 | 5.8 | Regulatory review added a step
INS-065 | Service Desk Portal Rollout | Replace the records used by Customer Service. | Customer Service | Q3-2026 | 2027-12-31 | No change | Execution | Initiation | 33.4 | 2026 | 20.9 | 2028 | 4.6
INS-066 | Safety Data Model Consolidation | Introduce the forecasting used by Finance. | Finance | 2027-01-22 | 2027-09-30 | 2028-03-31 | Execution | Execution | 35 | 2028 | 38.7 | 2029 |  |  | Resources moved to a higher-priority initiative | Reviewed at the quarterly portfolio meeting.
INS-067 | Inventory Dashboard Launch | Standardise the dashboard used by People. | People | 2024-06-12 | 2026-06-30 | Delivered | Delivered | Delivered | 43.1 | 2027 | 58.3 | 2026 | 2.4 | 1.8
INS-068 | Safety Scheduler Upgrade | Simplify the portal used by Technology. | Technology | 2024-11-14 | 2026-06-30 | Delivered | Delivered | Delivered |  |  |  |  | 2.8 | 2.6
INS-069 | Safety Forecasting Migration | Introduce the catalogue used by Supply Chain. | Supply Chain | 2026-07-21 | 2027-12-31 | No change | Execution | Initiation | 41.7 | 2027 | 35.9 | 2029 | 23.1 | 10.8
INS-070 | Service Desk Toolkit Upgrade | Standardise the portal used by Sales & Marketing. | Sales & Marketing | Q1-2026 | Q4-2026 | Cancelled | Delivered | Cancelled | 21 | 2026 |  |  | 17.8 | 4.2 | Testing found integration issues
INS-071 | Safety Portal Launch | Standardise the ledger used by Operations. | Operations | 2025-09-25 | 2026-03-31 | 2026-06-30 | Delivered | Execution | 19.2 | 2028 | 17.4 | 2027 | 25 | 16.4 | Resources moved to a higher-priority initiative
INS-072 | Asset Toolkit Redesign | Extend the forecasting used by Customer Service. | Customer Service | 2025 | 2026-06-30 | DELIVERED | Delivered | Delivered |  |  | 5.8 | 2026 | 16.1 | 9 |  | Reviewed at the quarterly portfolio meeting.
INS-073 | Onboarding Portal Migration | Standardise the portal used by Finance. | Finance | 2026-11-10 | 2027-06-30 | 2027-03-31 | Deployment | Execution | 4.7 | 2027 | 3.7 | 2028 | 16.3 | 10.7 | Resources moved to a higher-priority initiative
INS-074 | Purchasing Data Model Launch | Extend the catalogue used by People. | People | 2024-12-05 | 2026-06-30 | Delivered | Delivered | Delivered | 34.6 | 2026 | 45 | 2027 | 16.8 | 9.6
INS-075 | Onboarding Forecasting Automation | Standardise the workflow used by Technology. | Technology | Q2-2025 | 2026-11-30 | 2027-06-30 | Delivered | Execution | 2.9 | 2027 | 2.3 | 2027 | 13.7 | 8 | Supplier lead times longer than planned
INS-076 | Inventory Toolkit Launch | Replace the portal used by Supply Chain. | Supply Chain | 2025-04-09 | 2026-11-30 | Q2-2027 | Delivered | Execution |  |  |  |  | 1.4 | 0.5 | Faster delivery after reuse of an existing component
INS-077 | Customer Records Rollout | Standardise the forecasting used by Sales & Marketing. | Sales & Marketing | 2026-01-09 | Q4-2027 | No change | Execution | Initiation | 28.4 | 2026 | 18.8 | 2027 |  | 0.7
INS-078 | Warehouse Data Model Consolidation | Simplify the catalogue used by Operations. | Operations | 2026-01-25 | 2026-08-31 |  | Delivered | Deployment | 44.9 | 2028 | 48.9 | 2026 | 4 |  |  | Reviewed at the quarterly portfolio meeting.
INS-079 | Service Desk Data Model Rollout | Extend the data model used by Customer Service. | Customer Service | 2025-11-11 | 2026-08-31 |  | Delivered | Deployment | 26.5 | 2026 | 34.9 | 2028 | 17 | 15.8
INS-080 | Payroll Toolkit Modernisation | Simplify the forecasting used by Finance. | Finance | Q1-2025 | 2026-03-31 | Q3-2026 | Delivered | Execution |  |  | 7.1 | 2026 | 5.6 | 1.7 | Supplier lead times longer than planned
INS-081 | Payroll Portal Consolidation | Standardise the scheduler used by People. | People | 2026 | 2027-12-31 | CANCELLED | Initiation | Cancelled | 48.3 | 2027 | 58.1 | 2027 | 14.1 | 4.6 | Regulatory review added a step
INS-082 | Inventory Portal Consolidation | Replace the forecasting used by Technology. | Technology | 2026-05-21 | 2027-03-31 | 2027-01-31 | Deployment | Delivered | 8.8 | 2026 | 5.9 | 2027 | 9.8 | 5.1 | Scope extended after design review
INS-083 | Purchasing Ledger Automation | Extend the ledger used by Supply Chain. | Supply Chain | 2026-03-01 | 2027-12-31 | No change | Execution | Initiation | 47.6 | 2026 | 43.2 | 2027 | 10.9 | 2.5
INS-084 | Billing Catalogue Redesign | Replace the dashboard used by Sales & Marketing. | Sales & Marketing | 2026-03-06 | Q3-2027 | Q2-2028 | Execution | Execution |  |  |  |  | 13 | 7.4 | Scope extended after design review | Reviewed at the quarterly portfolio meeting.
INS-085 | Asset Ledger Redesign | Replace the catalogue used by Operations. | Operations | Q3-2025 | 2026-11-30 | 2027-01-31 | Delivered | Execution | 16 | 2026 | 10.2 | 2028 | 8 | 7.2 | Resources moved to a higher-priority initiative
INS-086 | Billing Catalogue Rollout | Extend the scheduler used by Customer Service. | Customer Service | 2025-09-01 | 2027-09-30 | 2027-12-31 | Execution | Execution | 18 | 2027 | 18.8 | 2029 | 18.3 | 3.7 | Regulatory review added a step
INS-087 | Purchasing Records Rollout | Simplify the dashboard used by Finance. | Finance | 2026-04-09 | 2027-06-30 | 2027-05-31 | Deployment | Execution | 35 | 2028 | 33.6 | 2029 | 24 | 18.8 | Supplier lead times longer than planned
INS-088 | Order Workflow Launch | Standardise the ledger used by People. | People | 2027-08-22 | 2028-03-31 |  | Initiation | Not started |  |  | 6.1 | 2028
INS-089 | Field Service Ledger Migration | Extend the toolkit used by Technology. | Technology | 2025-05-28 | 2026-08-31 |  | Delivered | Deployment | 4.2 | 2028 | 3 | 2026 | 7.3 | 3
INS-090 | Warehouse Workflow Migration | Replace the data model used by Supply Chain. | Supply Chain | 2026 | 2027-09-30 | 2028-02-29 | Execution | Execution | 4.2 | 2028 |  |  | 4.6 | 5.5 | Regulatory review added a step | Reviewed at the quarterly portfolio meeting.
INS-091 | Supplier Scheduler Redesign | Replace the data model used by Sales & Marketing. | Sales & Marketing | 2024-10-20 | Q1-2026 | On hold | Delivered | On hold | 53.1 | 2026 | 44.1 | 2026 | 9.3 |  | Regulatory review added a step
INS-092 | Onboarding Forecasting Migration | Replace the records used by Operations. | Operations | 2024-05-05 | 2026-03-31 | Q4-2026 | Delivered | Execution |  |  |  |  | 19.8 | 16.3 | Dependency on another initiative
INS-093 | Payroll Records Upgrade | Replace the scheduler used by Customer Service. | Customer Service | 2025-10-13 | 2026-06-30 | DELIVERED | Delivered | Delivered | 25.3 | 2026 | 23.1 | 2028 | 11.7 | 11.2
INS-094 | Reporting Workflow Automation | Extend the dashboard used by Finance. | Finance | 2024-06-04 | 2026-06-30 | Delivered | Delivered | Delivered | 54.3 | 2027 | 54 | 2026 | 12.2 | 6
INS-095 | Asset Scheduler Redesign | Standardise the records used by People. | People | Q4-2025 | 2027-12-31 | No change | Execution | Initiation | 16 | 2028 | 10.7 | 2029 | 2.7 | 1.8
INS-096 | Purchasing Catalogue Modernisation | Extend the records used by Technology. | Technology | 2025-07-04 | 2027-03-31 | Q1-2027 | Deployment | Delivered |  |  | 3 | 2026 | 2.7 | 1.5 | Faster delivery after reuse of an existing component | Reviewed at the quarterly portfolio meeting.
INS-097 | Customer Ledger Consolidation | Standardise the scheduler used by Supply Chain. | Supply Chain | 2026-12-12 | 2027-09-30 | 2028-05-31 | Execution | Execution | 32.5 | 2027 | 36.8 | 2026 | 17.4 | 13.4 | Testing found integration issues
INS-098 | Billing Scheduler Launch | Simplify the catalogue used by Sales & Marketing. | Sales & Marketing | 2024-03-16 | Q1-2026 | On hold | Delivered | On hold | 54 | 2027 | 65.2 | 2028 | 24 | 21.5 | Scope extended after design review
INS-099 | Safety Records Upgrade | Extend the portal used by Operations. | Operations | 2027 | 2027-12-31 | No change | Execution | Initiation | 50.8 | 2028 | 33.8 | 2027 |  | 1.6
INS-100 | Order Forecasting Modernisation | Replace the scheduler used by Customer Service. | Customer Service | Q4-2025 | 2027-09-30 | Q2-2028 | Execution | Execution |  |  |  |  | 14.1 | 8.9 | Regulatory review added a step

## Settings
Setting | Value
Reporting year | 2026
Status date | 2026-09-30
Currency | USD
Unit | millions
Grace period (months) | 3
Phase | Category
Not started | Not started
Initiation | In progress
Execution | In progress
Deployment | In progress
Delivered | Delivered
On hold | On hold
Cancelled | Cancelled

## Guidance
Column or topic | How to fill it
Steerline portfolio template | Fill in the Initiatives sheet (one row per initiative) and check the Settings sheet, then upload this file.
Required columns | Initiative ID, Initiative name, Business unit, Start, Baseline end, Planned phase at year end, Current phase. All other columns are optional.
Initiative ID | Required. Your own reference, up to 50 characters; must be unique in the file.
Initiative name | Required. Up to 200 characters.
Description | Optional free text, up to 2 000 characters.
Business unit | Required. Up to 100 characters. Used for the business-unit filter.
Start | Required. A date (YYYY-MM-DD or an Excel date), a quarter (Q1-2026 = 1 Jan 2026) or a year (2026 = 1 Jan 2026, marked as year only).
Baseline end | Required. A date or a quarter (Q4-2026 = 31 Dec 2026). Must not be before Start.
Revised end | Optional. A date or a quarter (not before Start), or one of: No change, Delivered, On hold, Cancelled. Leave blank if not revised.
Planned phase at year end | Required. A phase from the Settings sheet. Phases in the Delivered category make the initiative a year delivery target.
Current phase | Required. A phase from the Settings sheet.
Value baseline / Value revised | Optional amounts in the currency and unit on the Settings sheet. Not negative.
Value baseline / revised start year | Optional years (2000–2100). Shown next to the values; not used in calculations.
Approved budget (reporting year) | Optional amount for the reporting year. Blank counts as zero. Not negative.
Budget used or forecast | Optional amount. Blank counts as zero. Not negative.
Reason for change / Notes | Optional free text, up to 2 000 characters each.
Limits | Up to 500 initiatives and 1 MB per file. Files that fail validation are not saved.
Calculated values | Do not enter calculated values (status, delay, time elapsed, utilisation). They are worked out by Steerline from the columns above.
Settings | Reporting year, status date (the date your figures describe), currency, unit (optional, for example millions), grace period in whole months 0–24 before an initiative counts as overdue (blank = 3), and the phase list with a category for each phase. Phase names up to 60 characters; at least one phase must be in the Delivered category.
Sheets | The Initiatives and Settings sheets are required and their headers must not change. This Guidance sheet and any sheets you add are ignored.